## Product Backlog
Sprint | Product Goal | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S1 | Project foundation and requirements | US-001 | Understand the real-estate negotiation problem and define project scope, users, scenarios and outcomes. | MUST HAVE | None | All Team Members | Completed
S1 | Project foundation and requirements | US-002 | Provide Land / Plot, Apartment / Flat and Villa / Independent House scenarios. | MUST HAVE | US-001 | Akshaya | Completed
S1 | Project foundation and requirements | US-003 | Provide Aggressive, Collaborative and Risk-Averse personalities for negotiation agents. | MUST HAVE | US-001 | Akshaya | Completed
S1 | Project foundation and requirements | US-004 | Use a real-estate dataset and property filtering for realistic negotiation properties. | MUST HAVE | US-002 | Akshaya | Completed
S2 | Core multi-agent negotiation | US-005 | Create Buyer and Seller agents that negotiate property prices. | MUST HAVE | US-002, US-003 | Akshaya | Completed
S2 | Core multi-agent negotiation | US-006 | Create an Orchestrator Agent for turn-taking, history/context and round tracking. | MUST HAVE | US-005 | Akshaya | Completed
S2 | Core multi-agent negotiation | US-007 | Evaluate offers using ACCEPT, COUNTER and REJECT rules and controlled prices. | MUST HAVE | US-005 | Akshaya | Completed
S2 | Core multi-agent negotiation | US-008 | Use Gemini to generate contextual natural-language negotiation messages. | MUST HAVE | US-005, US-006, US-007 | Akshaya | Completed
S3 | Negotiation Arena and stability | US-009 | Build a chat-style Negotiation Arena showing turns, messages and reasoning. | MUST HAVE | US-006, US-008 | Sai Shankar,Divya Sri | Completed
S3 | Negotiation Arena and stability | US-010 | Detect repeated or stalled negotiations to prevent endless negotiation. | MUST HAVE | US-007 | Akshaya | Completed
S3 | Negotiation Arena and stability | US-011 | Display live stance indicators and round metrics. | SHOULD HAVE | US-009 | Srinivas,Divya Sri | Completed
S3 | Negotiation Arena and stability | US-012 | Connect the Negotiation Arena to the FastAPI backend APIs. | MUST HAVE | US-009 | Divya Sri | Completed
S4 | Outcome, reporting and final delivery | US-013 | Build Outcome Screen with final terms, concession timeline, rounds and objective satisfaction scores. | MUST HAVE | US-009, US-011, US-012 | Divya Sri | Completed
S4 | Outcome, reporting and final delivery | US-014 | Download the negotiation transcript and summary report. | SHOULD HAVE | US-013 | Ganesh | Completed
S4 | Outcome, reporting and final delivery | US-015 | Complete testing, technical documentation, project report and final demonstration. | MUST HAVE | US-010, US-012, US-013, US-014 | Akshaya,Srinivas,Sai shankar | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Members | Activity | Status | Original Estimate (Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-001 | 1 | Project introduction, problem understanding and requirement discussion | 22-Jul-2026 | 23-Jul-2026 | All Team Members | Others | Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Define scenarios and negotiation use cases | 24-Jul-2026 | 27-Jul-2026 | Akshaya, Srinivas | Analysis | Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | Define personality behavior and objectives | 28-Jul-2026 | 29-Jul-2026 | Akshaya | Design | Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 4 | Review dataset and implement property filtering | 30-Jul-2026 | 04-Aug-2026 | Akshaya | Data | Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | Implement Buyer and Seller agents | 05-Aug-2026 | 08-Aug-2026 | Akshaya | Coding | Completed | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 6 | Implement Orchestrator Agent and round tracking | 06-Aug-2026 | 11-Aug-2026 | Akshaya,Srinivas | Coding | Completed | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 7 | Implement counteroffer, concession and agreement evaluation | 09-Aug-2026 | 13-Aug-2026 | Akshaya | Coding | Completed | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 8 | Integrate Gemini reasoning engine and fallback | 10-Aug-2026 | 18-Aug-2026 | Akshaya | Integration | Completed | 18 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-009 | 9 | Build chat-style Negotiation Arena UI | 19-Aug-2026 | 24-Aug-2026 | Sai Shankar,Divya Sri | UI Development | Completed | 18 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-010 | 10 | Implement repeated-offer and stalled-negotiation deadlock handling | 20-Aug-2026 | 25-Aug-2026 | Akshaya | Testing/Coding | Completed | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 11 | Add live stance indicators and round metrics | 25-Aug-2026 | 01-Sep-2026 | Divya Sri,Srinivas | UI Development | In Progress | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 12 | Connect frontend Negotiation Arena to FastAPI APIs | 26-Aug-2026 | 01-Sep-2026 | Divya Sri,Srinivas | Integration | In Progress | 18 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-013 | 13 | Build Outcome Screen | 02-Sep-2026 | 08-Sep-2026 | Divya Sri,Srinivas | UI Development | In Progress | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 14 | Implement downloadable transcript and summary report | 04-Sep-2026 | 10-Sep-2026 | Ganesh | Coding | In Progress | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | 15 | System testing, documentation, report and final demo preparation | 08-Sep-2026 | 15-Sep-2026 | Akshaya,Srinivas Sai Shankar | Testing/Documentation | In Progress | 20 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0

## Stand-up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity about project scope and negotiation workflow. | Discussed requirements with the team and mentor and finalized the project scope.
Sprint 1 | Day 4 | Difficulty defining realistic real-estate negotiation scenarios. | Conducted brainstorming and finalized the three property scenarios.
Sprint 1 | Day 8 | Dataset fields needed to be mapped to scenarios. | Reviewed the dataset and implemented property classification/filtering.
Sprint 2 | Day 3 | Unclear responsibility of the Orchestrator Agent. | Defined turn-taking, history/context passing and round tracking.
Sprint 2 | Day 6 | Buyer and Seller counteroffer behavior was inconsistent. | Reviewed evaluator rules and enforced upward Buyer and downward Seller movement.
Sprint 2 | Day 10 | Gemini/API availability issues. | Added deterministic fallback responses and kept price decisions under evaluator control.
Sprint 3 | Day 3 | UI needed to match the actual backend flow. | Connected the Negotiation Arena design to real project data.
Sprint 3 | Day 7 | Repeated offers could cause endless negotiation. | Improved repeated-offer and stalled-negotiation deadlock handling.
Sprint 3 | Day 10 | Need meaningful live round metrics. | Reviewed offer, round and stance data for the metrics panel.
Sprint 4 | Day 3 | Outcome Screen needed final negotiation state data. | Mapped final status, agreed price, history and rounds to the outcome view.
Sprint 4 | Day 7 | Transcript and report needed a consistent format. | Implemented downloadable transcript and summary report generation.

## Retrospection
S.No. | Sprint | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 22-Jul-2026 | 04-Aug-2026 | Akshaya | Document requirements clearly. | Making assumptions about unclear requirements. | Discussing requirements with the team. | Kept project scope and decisions aligned.
2 | Sprint 1 | 22-Jul-2026 | 04-Aug-2026 | Akshaya,Srinivas | Break large requirements into user stories. | Delaying questions about unclear use cases. | Participating in brainstorming. | Helped finalize scenarios and use cases.
3 | Sprint 2 | 05-Aug-2026 | 18-Aug-2026 | Akshaya,Ganesh | Validate negotiation rules with test cases. | Treating close prices as agreement. | Reviewing evaluator behavior. | Validated exact-price agreement and counteroffer rules.
4 | Sprint 2 | 05-Aug-2026 | 18-Aug-2026 | Srinivas,Akshaya | Test agent behavior after major changes. | Waiting until the end for integration testing. | Supporting backend debugging. | Performed agent and negotiation-flow checks.
5 | Sprint 3 | 19-Aug-2026 | 01-Sep-2026 | Srinivas,Divya Sri,Sai Shankar | Test UI changes with real backend responses. | Using hardcoded demo values in connected screens. | Improving the chat-style arena. | Aligned UI behavior with actual negotiation data.
6 | Sprint 3 | 19-Aug-2026 | 01-Sep-2026 | Srinivas,Divya Sri,Ganesh | Track useful round metrics early. | Adding metrics without checking usefulness. | Reviewing UI clarity. | Planned stance indicators and round metrics.
7 | Sprint 4 | 02-Sep-2026 | 15-Sep-2026 | Divya Sri | Validate final screens using completed negotiations. | Treating close prices as successful agreement. | Keeping documentation aligned with implementation. | Prepared Outcome Screen, reports and final documentation.
8 | Sprint 4 | 02-Sep-2026 | 15-Sep-2026 | Akshaya,Divya Sri,Srinivas Ganesh,Sai Shankar | Start final integration and demo checks earlier. | Leaving screenshots and report work until the final day. | Communicating blockers during stand-ups. | Scheduled final testing, documentation and demonstration preparation.